## Projects
Project ID | Project Name | Status | Start Date | End Date | Planned Budget | Planned Revenue | Sellable Area | Units Count
P001 | Budva Residence | Pause | 2026-04-10 | 2026-04-21 | 8500000 | 12000000 | 3500 | 42
P002 | Bar Residence | Construction | 2026-04-07 | 2026-04-24 | 129000 | 1500000 | 2000 | 12
P003 | Ulcin Residence | Construction | 2025-12-31 | 2027-03-27 | 239000 | 2323200 | 3000 | 14

## Units
Unit ID | Project ID | Type | Number | Floor | Area | Status
U001 | Budva Residence | Apartment | A-12 | 1 | 65 | Available
U002 | Budva Residence | Pakinkg | A-13 | 1 | 4 | Reserved
U003 | Budva Residence | Apartment | A-14 | 3 | 12 | Sold
U004 | Ulcin Residence | Apartment | A-15 | 5 | 65 | Sold
U005 | Bar Residence | Pakinkg | A-16 | 6 | 55 | Sold
U006 | Budva Residence | Apartment | A-17 | 7 | 100 | Sold
U007 | Budva Residence | Commercial | A-18 | 9 | 45 | Sold
U008 | Budva Residence | Apartment | A-19 | 2 | 76 | Available
U009 | Bar Residence | Apartment | A-20 | 1 | 34 | Available
U010 | Budva Residence | Apartment | A-21 | 3 | 65 | Sold
U011 | Budva Residence | Apartment | A-22 | 3 | 65 | Sold
U012 | Bar Residence | Pakinkg | A-23 | 3 | 56 | Reserved
U013 | Ulcin Residence | Apartment | A-24 | 5 | 65 | Reserved
U014 | Ulcin Residence | Pakinkg | A-25 | 3 | 65 | Reserved
U015 | Ulcin Residence | Apartment | A-26 | 6 | 89 | Available
U016 | Bar Residence | Apartment | A-27 | 3 | 65 | Available
U017 | Budva Residence | Pakinkg | A-28 | 1 | 45 | Available
U018 | Bar Residence | Apartment | A-29 | 3 | 65 | Sold

## Clients
Client ID | Name | Phone | Email | Notes
C001 | Agne Durakovic | +382... | email@mail.com
C002 | Alexabder Sagalovic | +382... | email@mail.com
C003 | Alexander Sagalovich | +382... | email@mail.com
C004 | Amar I Mersudin Prentic | +382... | email@mail.com
C005 | Amir Bajramovic | +382... | email@mail.com
C006 | Anastazija Glavicic | +382... | email@mail.com
C007 | Avdulah Destanovic | +382... | email@mail.com
C008 | Balic Esad | +382... | email@mail.com
C009 | Biljana Djikanovic Milic | +382... | email@mail.com
C010 | Bogavac Aleksandra | +382... | email@mail.com
C011 | Bojadžić Sead | +382... | email@mail.com
C012 | Branimir Lakicevic | +382... | email@mail.com
C013 | Bulatović Goran | +382... | email@mail.com
C014 | Bulatovic Sinisa | +382... | email@mail.com

## Sales
Sale ID | Client ID | Project ID | Unit ID | Price | Price m2 | Reserve Date | Contract Date | Status | Trello | Column 1 | Column 2 | Column 3 | Column 4 | Column 5 | Column 6 | Column 7 | Column 8
S001 | C001 | P001 | U001 | 1200000 | 2000 | 2025-12-01 | 2025-12-01 | Signed
S002 | C002 | P001 | U002 | 950000 | 1900 | 2025-12-05 | 2025-12-05 | Signed
S003 | C003 | P001 | U003 | 1500000 | 2100 | 2026-01-10 | 2026-01-10 | Signed
S004 | C004 | P002 | U010 | 1100000 | 1800 | 2026-02-01 | 2026-02-01 | Signed
S005 | C005 | P002 | U011 | 1300000 | 2000 | 2026-02-15 | 2026-02-15 | Signed
S006
S007
S008
S009
S010
S011
S012
S013
S014
S015
S016
S017
S018
S019

## Payment Allocations
Payment ID | Sale ID | Client | Allocated | Date
P001 | S001 | C001 | 1200000 | 2026-02-11
P002 | S002 | C002 | 950000 | 2026-02-12
P005 | S004 | C004 | 1100000 | 2026-04-05
P007 | S003 | C003 | 1000000 | 2026-03-12
P012 | S003 | C003 | 500000 | 2026-02-10

## Client Payments
Payment ID | Date | Client | Unit | Payment Info | Amount | Method | Reference | Confirmed
P001 | 2026-02-11 | C001 | U002 | Agne Durakovic [Budva Residence] | 10000000 | Bank |  | Yes
P002 | 2026-02-12 | C002 | U001 | Alexabder Sagalovic [Budva Residence] | 20000000 | Bank |  | Yes
P003 | 2026-02-18 | C001 | U004 | Agne Durakovic [Ulcin Residence] | 3000000 | Bank |  | Yes
P004 | 2026-04-04 | C002 | U005 | Alexabder Sagalovic [Bar Residence] | 1000000 | Bank |  | Yes | payment example
P005 | 2026-04-05 | C004 | U005 | Amar I Mersudin Pren [Bar Residence] | 2000000 | Bank |  | Yes
P006 | 2026-04-06 | C006 | U006 | Anastazija Glavicic [Budva Residence] | 3000000 | Bank |  | Yes
P007 | 2026-03-12 | C003 | U010 | Alexander Sagalovich [Budva Residence] | 1000000 | Bank |  | Yes
P008 | 2026-04-08 | C001 | U003 | Agne Durakovic [Budva Residence] | 1500000 | Bank |  | Yes
P009 | 2026-02-12 | C004 | U006 | Amar I Mersudin Pren [Budva Residence] | 1000000 | Bank |  | Yes
P010 | 2026-04-10 | C004 | U001 | Amar I Mersudin Pren [Budva Residence] | 1500000 | Bank |  | Yes
P011 | 2026-04-11 | C001 | U002 | Agne Durakovic [Budva Residence] | 1000000 | Bank |  | Yes
P012 | 2026-02-10 | C003 | U003 | Alexander Sagalovich [Budva Residence] | 2000000 | Bank |  | Yes
P013 | 2026-04-13 | C003 | U004 | Alexander Sagalovich [Ulcin Residence] | 3000000 | Bank |  | Yes
P014 | 2026-01-15 | C001 | U003 | Agne Durakovic [Budva Residence] | 10000000 | Bank |  | Yes
P015 | 2025-12-03 | C008 | U013 | Balic Esad [Ulcin Residence] | 15000000 | Bank |  | Yes
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Budget
Budget ID | Project | Category | Unit | Qty | Price | Total (Estimated) | Total (Real) | Difference
B001 | P001 | I PRIPREMNI RADOVI | m3 | 400 | 120 | 29474 | 30000 | -526
B002 | P001 | II ZEMLJANI RADOVI |  |  |  | 281551.9725 | 295555 | -14003.0275
B003 | P001 | III BETONSKI I ARM. BETONSKI RADOVI |  |  |  | 1662203.302 | 1500000 | 162203.302
B004 | P001 | IV ARMIRAČKI RADOVI |  |  |  | 1465972.256 | 1465972.256 | 0 | ESTIMATED | REAL | BALANCE
B005 | P001 | V ČELIČNI RADOVI |  |  |  | 3798.16 | 3700.8437 | 97.3163 | 8853393.038 | 8678212.336 | 175180.7017
B006 | P001 | VI ZIDARSKI RADOVI |  |  |  | 887552.6076 | 876679.4581 | 10873.1496
B007 | P001 | VII IZOLATERSKI RADOVI |  |  |  | 462255.9408 | 443925.5644 | 18330.3764
B008 | P001 | VIII FASADNA BRAVARIJA |  |  |  | 372880 | 373892.1647 | -1012.1647
B009 | P001 | IX BRAVARSKI RADOVI |  |  |  | 505675 | 489000.7369 | 16674.2631
B010 | P001 | X STOLARSKI RADOVI |  |  |  | 84100 | 84683.4746 | -583.4746
B011 | P001 | XI LIMARSKI RADOVI |  |  |  | 56612.5 | 55542.4335 | 1070.0665
B012 | P001 | XII PODOPOLAGAČKI RADOVI |  |  |  | 366640 | 371751.5273 | -5111.5273
B013 | P001 | XIII KERAMIČARSKI RADOVI |  |  |  | 162493 | 165943.3604 | -3450.3604
B014 | P001 | XIV KAMENOPOLAGAČKI RADOVI |  |  |  | 103905.0135 | 102646.1288 | 1258.8847
B015 | P001 | XV FASADERSKI RADOVI |  |  |  | 133551.867 | 132582.1727 | 969.6943
B016 | P001 | XVI SUVOMONTAŽNI RADOVI |  |  |  | 289779.3 | 303043.7892 | -13264.4892
B017 | P001 | XVII MOLERSKO-FARBARSKI RADOVI |  |  |  | 282510.9424 | 276265.6881 | 6245.2543
B018 | P001 | XVIII LIFTOVSKA POSTROJENJA |  |  |  | 120000 | 118091.5701 | 1908.4299
B019 | P001 | XIX RAZNI ZANATSKI RADOVI |  |  |  | 13323 | 13708.3201 | -385.3201
B020 | P001 | XX ZAVRŠNI RADOVI |  |  |  | 15475 | 15421.5678 | 53.4322
B021 | P001 | XXI KLIMATIZACIJA I VENTILACIJA |  |  |  | 398324.75 | 382731.5586 | 15593.1914
B022 | P001 | XXII JAKA STRUJA |  |  |  | 607493.32 | 617661.0486 | -10167.7286
B023 | P001 | XXIII JAKA STRUJA GARAZA |  |  |  | 27713.6 | 28098.1714 | -384.5714
B024 | P001 | XXIV VIO |  |  |  | 121212 | 122412.6838 | -1200.6838
B025 | P001 | XXV SPRINKLER |  |  |  | 84808 | 87417.3742 | -2609.3742
B026 | P001 | XXVI SAOBRACAJ |  |  |  | 38686.746 | 37570.8217 | 1115.9243
B027 | P001 | XXVII SIGNALIZACIJA |  |  |  | 4589.2 | 4805.8518 | -216.6518
B028 | P001 | XXVIII SLABA STRUJA |  |  |  | 258478.56 | 267025.8686 | -8547.3086
B029 | P001 | XXIX VODOVOD I KANALIZACIJA |  |  |  | 12333 | 12082.9011 | 250.0989

## Contractors
Contractor ID | Name | Phone | Email | Notes | Column 1 | Column 2
CTR1 | Дима | 911 | some@gmail.com | Дима
CTR2 | Слава | 911 | some@gmail.com
CTR3 | Мага | 911 | some@gmail.com

## Contracts
Contract ID | Project ID | Contractor Name | Contract Name | Contract Amount | Paid | Remaining | % Complete | Status | Trello
D1 | CTR1 | Дима | Rough works | 100000 | 400000 | -300000 | 400% | Completed
D2 | CTR2 | Слава | Electrics | 120000 | 100000 | 20000 | 83.33% | Active
D3 | CTR3 | Мага | Facade | 150000 | 100000 | 50000 | 66.67% | Active
D4 | CTR1 | Дима | Electrics | 100000 | 100000 | 0 | 100% | Completed
D5 |  | #N/A |  |  | 0 | 0 | 0% | Active
D6 |  | #N/A |  |  | 0 | 0 | 0% | Active
D7 |  | #N/A |  |  | 0 | 0 | 0% | Active
D8 |  | #N/A |  |  | 0 | 0 | 0% | Active
D9 |  | #N/A |  |  | 0 | 0 | 0% | Active
D10 |  | #N/A |  |  | 0 | 0 | 0% | Active
D11 |  | #N/A |  |  | 0 | 0 | 0% | Active
D12 |  | #N/A |  |  | 0 | 0 | 0% | Active
D13 |  | #N/A |  |  | 0 | 0 | 0% | Active
D14 |  | #N/A |  |  | 0 | 0 | 0% | Active
D15 |  | #N/A |  |  | 0 | 0 | 0% | Active
[5 empty] | 0 | 0 | 0% | Active
[5 empty] | 0 | 0 | 0% | Active

## Expenses
Expense ID | Date | Project | Contractor | Contract | Category | Amount | Status | Payment Date | Verification
EX1 | 2026-04-21 | P001 | CTR1 | D1 | II ZEMLJANI RADOVI | 100000 | Paid | 2026-02-12 | Verified
EX2 | 2026-04-22 | P002 | CTR2 | D2 | III BETONSKI I ARM. BETONSKI RADOVI | 100000 | Paid | 2026-03-03 | Verified
EX3 | 2026-04-23 | P001 | CTR1 | D1 | II ZEMLJANI RADOVI | 200000 | Paid | 2026-02-12 | Verified
EX4 | 2026-04-24 | P001 | CTR1 | D1 | I PRIPREMNI RADOVI | 100000 | Paid | 2026-04-17 | Verified
EX5 | 2026-05-04 | P002 | CTR3 | D3 | VI ZIDARSKI RADOVI | 100000 | Paid | 2026-04-19 | Verified
EX6 | 2026-05-04 | P001 | CTR3 | D4 | I PRIPREMNI RADOVI | 100000 | Paid | 2026-04-20 | Verified
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Receivables
Client | Project | Unit | Sale | Paid | Outstanding | Status | Column 8
C001 | P001 | U001 | 1200000 | 25500000 | -24300000 | Paid
C002 | P001 | U002 | 950000 | 21000000 | -20050000 | Paid
C003 | P001 | U003 | 1500000 | 6000000 | -4500000 | Paid
C004 | P002 | U010 | 1100000 | 4500000 | -3400000 | Paid
C005 | P002 | U011 | 1300000 | 0 | 1300000 | Unpaid

## Bank Accounts
Account ID | Name | Bank | Currency | Balance | Updated
ACC001 | Main Account | CKB | EUR | 350000 | 01.04.2026

## Cash Flow
Month | Opening | Income | Expense | Net | Closing | Verifying
2025-12-01 | 0 | 15000000 | 0 | 15000000 | 15000000 | TRUE
2026-01-01 | 15000000 | 10000000 | 0 | 10000000 | 25000000 | TRUE
2026-02-01 | 25000000 | 36000000 | 300000 | 35700000 | 60700000 | TRUE
2026-03-01 | 60700000 | 1000000 | 100000 | 900000 | 61600000 | TRUE
2026-04-01 | 61600000 | 13000000 | 300000 | 12700000 | 74300000 | TRUE

## VAT
Month | Project ID | Incoming VAT | Outgoing VAT | VAT Payable | Cumulative VAT | Type
2025-12-01 | C008 | 0 | 2603305.7851 | 2603305.7851 | 2603305.7851 | Payable
2026-01-01 | C001 | 0 | 1735537.1901 | 1735537.1901 | 4338842.9752 | Payable
2026-02-01 | P001 | 52066.1157 | 0 | -52066.1157 | 4286776.8595 | Refund
2026-02-01 | C001 | 0 | 2256198.3471 | 2256198.3471 | 6542975.2066 | Payable
2026-02-01 | C002 | 0 | 3471074.3802 | 3471074.3802 | 10014049.5868 | Payable
2026-02-01 | C004 | 0 | 173553.719 | 173553.719 | 10187603.3058 | Payable
2026-02-01 | C003 | 0 | 347107.438 | 347107.438 | 10534710.7438 | Payable
2026-03-01 | P002 | 17355.3719 | 0 | -17355.3719 | 10517355.3719 | Refund
2026-03-01 | C003 | 0 | 173553.719 | 173553.719 | 10690909.0909 | Payable
2026-04-01 | P001 | 34710.7438 | 0 | -34710.7438 | 10656198.3471 | Refund
2026-04-01 | P002 | 17355.3719 | 0 | -17355.3719 | 10638842.9752 | Refund
2026-04-01 | C002 | 0 | 173553.719 | 173553.719 | 10812396.6942 | Payable
2026-04-01 | C004 | 0 | 607438.0165 | 607438.0165 | 11419834.7107 | Payable
2026-04-01 | C006 | 0 | 520661.157 | 520661.157 | 11940495.8678 | Payable
2026-04-01 | C001 | 0 | 433884.2975 | 433884.2975 | 12374380.1653 | Payable
2026-04-01 | C003 | 0 | 520661.157 | 520661.157 | 12895041.3223 | Payable

## Dashboard
PROJECT OVERVIEW
Total Projects | 3
Active Projects | 2
Completed Projects | 0
SALES & CLIENTS
Total Sales Value | 6050000
Received from Clients | 75000000
Outstanding | -68950000
Sales → сколько продали (Revenue)
EXPENSES & CONTRACTS |  | Payments → сколько получили (Cash)
Total Budget | 8678212.3361 | Expenses → сколько потратили
Contracted Amount | 470000 | Bank → сколько денег сейчас
Paid to Contractors | 700000
Remaining Budget | 7978212.3361
CASH POSITION
Total Cash | 350000
Receivables | 75000000
Payables | 700000
Net Cash | 350000
PROFITABILITY
Revenue | 6050000
Expenses | 700000
Profit | 5350000
ROI | 0.60329
VAT OVERVIEW
Current VAT Payable | 121487.6033
Total Incoming VAT | 13016528.9256
Total Outgoing VAT | 12895041.3223
Cumulative VAT | 470000
700000
-230000
0.054159
UPDATE DASHBOARD